## Consolidated Summary Report
Date of Report:
[Relevant Business - see below comment] | [12 empty] | (FY14) Financial Benefit |  |  |  |  | (FY15) Benefit | (FY16) Benefit
F4B ID | Business | Idea Title | Sponsor | Project Manager | Status | Targeted Benefit ($m) | Expected Benefit ($m) | Energy Savings ? (Y/N) | Start Date | Completion Date | Status (RAG) | Status Description | Expected Gross FY14 Benefit ($m) | Expected FY14 Opex costs ($m) | Net FY14 Benefit ($m) | FY14 Capex ($m) | Net Cashflow Impact ($m) | Expected Incremental Gross FY15 Benefit ($m) | Expected Incremental Gross FY16 Benefit ($m)
Refer notes within cells above.
One row for each initiative.
This Consolidated Summary Report needs to be able to be run at various levels. Ie. at Total DI level, at DI East Level, at RISE level and at RISE VIC level.
The Organsiational structure to be set up within the tool which will be a form of a drop down box to select the relevant business will be provided.
The phasing of the years and how this 'rolls over' at the end of each financial year will need to be discussed. This will also impact the monthly update section of the online tool.
All $ amounts are to be incremental so will need the calculations in the background to do this. Will need to talk through this.
Totals for the $ columns as per below.
Total
Note on I4: Simon Kerry: This is status from tool such as Submitted, Approved, Closed etc)
Note on J4: Simon Kerry: This is from Project Set Up and is fixed at point of Business Case - doesn’t change
Note on K4: Simon Kerry: This is latest expected benefit $'s from the Execution Reassessment
Note on L4: Simon Kerry: Need to include new tick box for this in the tool
Note on S4: Simon Kerry: Calculation
Note on U4: Simon Kerry: Calculation

## Individual Project Dashboard
Project Dashboard
Idea Title | [5 empty] | Business Unit |  |  | Start Date |  | Initiative Status
Initiative Sponsor | [5 empty] | Initiative Manager |  |  | End Date |  | Benefit Type(s)
Status Description | [8 empty] | Milestone Plan and Tracking
Milestone date
[10 empty] | Upcoming Milestones |  | Plan | Update/ actual | Status
1
2
3
Initiative Financials |  | Plan |  |  | Reassessment |  |  |  | 4
($'000s) |  | Year 1 | Year 2 | Year 3 | Year 1 |  | Year 2 | Year 3
Gross Benefits | [8 empty] | 5
- Labour
- Asset / Plant | [8 empty] | 6
- Energy
- Overhead | [8 empty] | 7
- Procurement
Total | [8 empty] | 8
Opex | [8 empty] | 9
Capex
Initiative Status | [8 empty] | Key Achievements
Item | Status | Last month | Issues |  |  |  | Mitigations |  | 1
Overall Initiative Status | R | G | [6 empty] | 2
3
Benefits Realisation | A | A | [6 empty] | 4
5
Schedule Attainment | A | R | [6 empty] | Corrective Actions required |  |  |  | Date Due
1
Budget Attainment | R | R | [6 empty] | 2
3
Look at resizing the sections above (Milestones, Key Achievements, Corrective Actions depending on how many
of each there are for each initiative.
| Jan | 2011
| Feb | 2012
| Mar | 2013
| Apr | 2014
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
These numbers will be colored in either Green, Orange or Red
depending on their comparison to the adjacent Plan
numbers.
Green if benefit number is within 10% or higher than Plan
number. Orange if 10% to 20% less than plan and Red if more
than . 20% below plan. Opposite for Opex and Capex colors.
Direct update from tracking tool
The issues and Mitigations for each of the item categories
will come from the monthly update in the tool. New sections
within Project Data input section need to be included in the
tool to capture RAG for each. Will go above benefits
reassessment. The categorisation of the issue as per the tool
(currently called Project Risks - being changed to Issues)
will drive which 'Item' on the left the Issue and mitigations
will be put against.
Need to discuss how this works and whether changes to the
tool will be needed. What we may need to change is
functionality so can comapre original due date with
revised due date. Not sure we need the status against each
milestone as wont have this data captured. Also probably
covered through RAG for Schedule Attainment on the left
These numbers will come from
Project Set Up and will not
change once the Project moves
to Execution
Include most recent achievements at top and then go down
as far as will fit in the space available
Include most recent corrective actions at top
MB - I thought that the CARs would be the Mitigations in the status box - hence no need for this section.
Note on C14: Simon Kerry: This comes from Project Set up and will not change once project commences
Note on F14: Simon Kerry: This will pick up latest updated numbers from the Execution section of the tool

## Benefits Type Report
Benefits type report - [Business] | [7 empty] | Benefits (FY14) | [5 empty] | Benefits (FY15) | [5 empty] | Benefits (FY16)
F4B ID | Business | Idea Title | Project Manager | Status | Targeted Benefit ($m) | Expected Benefit ($m) | Status (RAG) | Labour ($m) | Asset / Plant $m | Energy $m | Procurement $m | Overhead $m | Total $m | Labour ($m) | Asset / Plant $m | Energy $m | Procurement $m | Overhead $m | Total $m | Labour ($m) | Asset / Plant $m | Energy $m | Procurement $m | Overhead $m | Total $m
Refer notes within cells above.
One row for each initiative.
This Benefits Type Report needs to be able to be run at various levels. Ie. at Total DI level, at DI East Level, at RISE level and at RISE VIC level.
The Organsiational structure to be set up within the tool which will be a form of a drop down box to select the relevant business will be provided.
The phasing of the years and how this 'rolls over' at the end of each financial year will need to be discussed. This will also impact the monthly update section of the online tool.
All $ amounts are to be incremental so will need the calculations in the background to do this. Will need to talk through this.
Totals for the $ columns as per below.
Total
Note on H4: Simon Kerry: This is status from tool such as Submitted, Approved, Closed etc)
Note on I4: Simon Kerry: This is from Project Set Up and is fixed at point of Business Case - doesn’t change
Note on J4: Simon Kerry: This is latest expected benefit $'s from the Execution Reassessment

## Summary Dashboard Report
This report is a summary report that needs to be able to be run for a specific business at the RISE level, East Level and DI level. Not at any level below RISE
The below doesn’t reflect the ideal format but just the key components to be included in the dashboard. Ideally to fit on one page.
Business: |  |  | Date:
1. Pie Chart of Number of initiatives showing breakdown by status of initiative - drawn from status in online tool.
2. Pie chart showing $ benefits broken down by status of initiative - drawn from status in online tool.
3. Pie chart showing number of initatives by next level down business units. Ie. For RISE report it will show breakdown by RISE businesses. For DI East
report it will show breakdown by DI East businesses such as RISE, RINE, EC&S, Rail, DI Corp. Will need to work through mechanics of hierarchies.
4. Pie chart showing breakdown of $ benefits (current year) by next level down business units. Ie. For RISE report it will show breakdown by RISE businesses. For DI East
report it will show breakdown by DI East businesses such as RISE, RINE, EC&S, Rail, DI East Corp. Will need to work through mechanics of hierarchies.
5. Summary Table:
Initiative Financials | Plan |  |  | Current Reassessment
($'000s) | Year 1 | Year 2 | Year 3 | Year 1 | Year 2 | Year 3
Gross Benefits
- Labour
- Asset / Plant
- Energy
- Overhead
- Procurement
Total
Opex
Capex
6. Some type of monthly trend chart showing month to month bar chart of total Expected benefits and number of initiatives with benefit over 3 year horizon
At beginning we will just have one month but will then extend out as we start using the online tool to show trend in $ benefits and numbers of benefits.
Query whether we need this analysis at sub business level and not just at consolidated level.
7. % of [Submitted] and [Underway] initiatives that have had no activity for >40 days by business
These numbers will be colored in either Green, Orange or Red
depending on their comparison to the adjacent Plan
numbers.
Green if benefit number is within 10% or higher than Plan
number. Orange if 10% to 20% less than plan and Red if more
than 20% below plan. Opposite for Opex and Capex colors
These numbers will come from
Project Set Up and will not
change once the Project moves
to Execution
Note on C24: Simon Kerry: This comes from Project Set up and will not change once project commences
Note on F24: Simon Kerry: This will pick up latest updated numbers from the Execution section of the tool

## Consolidated Closure Report
Project Summary |  |  |  |  | Benefit Achieved ($m) | [5 empty] | Energy Savings Analysis |  |  | Opportunity
F4B ID | Business | Idea Title | Project Manager | Targeted Benefit ($m) | Benefit Achieved ($m) | Labour ($m) | Asset / Plant $m | Energy $m | Procurement $m | Overhead $m | Energy Savings Type | Energy Savings Unit | Energy Savings Amount | Further Oppportunities identified | Leverage to Other Businesses | Lessons Learned
Total of cells J to N
Refer notes within cells above.
This could/should be an extension of the consolidated Summary Report and should be a standard report rather than custom
Need to enable multi lines for an initiative based on itemised energy/leverage/lessons
Filter by project size or individual impacts of a particular benefit
Need to carefully define savings (per year, once off, sustainable)
Total
Direct input from tool with enough lines per project to capture data. Should be based on drop down in tool if possible
Direct input from tool with enough lines per project to capture data. Will need to be free text in tool but may need some method of categorising for future analysis
Direct input from tool with enough lines per project to capture data. Should be based on drop down in tool if possible
Note on H4: Simon Kerry: This is from Project Set Up and is fixed at point of Business Case - doesn’t change
Note on I4: Simon Kerry: This is final benefit $'s achieved from the Project completion
Note on O4: Simon Kerry: To come from new section in Project Completion
Note on P4: Simon Kerry: This will come from new section in Project Completion
Note on Q4: Simon Kerry: This will come from new section to be inlcuded in Proejct Completion

## Business Unit Heirarchy
Level 1 | Level 2 | Level 3 | Level 4
Downer Infrastructure | Downer Infrastructure East and West | RINE | Queensland
New South Wales
ACT/Southern New South Wales
Airports
Plant
Overhead
|  | RISE | Victoria/Tasmania
South Australia/Northern Territory
Bitminous Products
Western Australia
Plant
Overhead
|  | ECS | Queensland
New South Wales
South East Australia
Western Australia
Plant
Overhead
|  | West | Major Projects (Civils)
Plant
Overhead
|  | Rail | Projects
Operations
Plant
Overhead
|  | Downer Mouchel JV | Western Australia
Queensland
New South Wales
|  | Clough Downer JV | Queensland
Western Australia
| Specialist Services | Renewables
Transmission
Foxtel
NBN
Telco
Plant
Overhead
| Infrastructure Services | Snowden
Mineral Technologies
QCC
Asset Management
Plant
Overhead
Corporate
Shared Services
Need to confirm with the businesses through the F4B Reps
Do we need to go to Level 4 for SS and IS or level 3 for Group functions given size of HR, ZH and Finance?
Do we need PMO and BD separated?

## Energy Categories
Mobile Fleet
Use | Type | Unit
Transport | Petrol | litres | Includes ethanol blends
| Diesel | litres
| Biofuels | litres | Define type (text)
| LPG | litres | Define butane or propane
Stationary | Diesel | litres
| Natural Gas | GJ
| LPG | litres | Define butane or propane
| Autogas | litres
| Fuel Oil | litres
Electricity (Mains) | Electricity | kWh
Electricity (Generator) | Diesel | litres